## Requirements Traceability
Team Name |  | Project Manager
HyperTechs |  | Emmanuel Martinez
Requirement ID | Requirements | Test Case Description | Status | Comments
1 | Admin must be able to log in | Admin Log in | Successful | Jan 4: Testing started Jan 11: Error reported Jan 18: Admin can’t log in yet Jan 19: Admin can successfully log in now
2 | Admin must be able to register | Create registration | Successful | Jan 4: Testing started Jan 11: Error reported Jan 18: Still cannot create an account. Jan 19: Admin can successfully register now
3 | Admin must enter OTP to be verified | Admin Log in with OTP | Successful | Jan 13: Testing started Jan 14: Error reported Jan 19: Admin can successfully log in, but there is no SMS for OTP yet; it is still console-based Jan 26: Admin can successfully log in now with OTP
4 | The account balance will be displayed, indicating whether it is sufficient or not, during deposit and withdrawal transactions. | Account balance will be displayed | Successful | Jan 24: Testing started Jan 25: Error reported Jan 26: The account balance feature is now successful
5 | Deposit | Process customer deposit | Successful | Jan 4: Testing started Jan 18: Still in progress Jan 19: The deposit feature is now working successfully.
6 | Withdrawal | Withdrawal Processing | Successful | Jan 4: Testing started Jan 18: Still in progress Jan 19: The withdrawal feature is now working successfully.
7 | Admin must be able to view withdrawal and deposit history | Transaction Viewing History | Successful | Jan 16: Testing started Jan 17: Still in progress Jan 18: An error occurs; cannot view the transaction history. Jane 19: Admin can now view the transaction history feature successfully.
8 | Admin must be able to use the forgot password feature and reset the password | Verify forgot password functionality | Successful | Jan 13: Testing started Jan 15: Error occurs Jan 18: The error has been fixed. The Forgot Password feature is already functioning well, both in terms of OTP generation and password reset.
9 | The admin must have the ability to log out, with a confirmation prompt. | Log out | Successful | Jan 18: Started testing Jan 19: Admin can successfully log out now, but the confirmation prompt is not yet enabled. Jan 27: The admin can now successfully log out with a logout confirmation. This confirmation informs that logging out will terminate the current session, and users will need to reauthenticate to access their account again.
Requirements Traceability
Matrix