## Requirements Traceability
Team Name |  | Project Manager
HyperTechs |  | Emmanuel Martinez
Requirement ID | Requirements | Test Case Description | Status | Comments
1 | Admin must be able to log in | Admin Log in | Successful | Jan 4: Testing started Jan 11: Error reported Jan 18: I can’t log in yet Jan 19: I can successfully log in now
2 | Admin must be able to register | Create registration | Successful | Jan 4: Testing started Jan 11: Error reported Jan 18: I still cannot create an account. Jan 19: I can successfully register now
3 | Admin must enter OTP to be verified | Admin Log in with OTP | In-progress | Jan 13: Testing started Jan 14: Error reported Jan 19: I can successfully log in, but there is no SMS for OTP yet; it is still console-based
4 | Deposit | Process customer deposit | Successful | Jan 4: Testing started Jan 18: Still in progress Jan 19: The deposit feature is now working successfully.
5 | Withdrawal | Withdrawal Processing | Successful | Jan 4: Testing started Jan 18: Still in progress Jan 19: The withdrawal feature is now working successfully.
6 | Admin must be able to view withdrawal and deposit history | Transaction Viewing History | Successful | Jan 16: Testing started Jan 17: Still in progress Jan 18: An error occurs; cannot view my transaction history. Jane 19: I can now view the transaction history feature successfully.
7 | Admin must be able to use the forgot password feature and reset the password | Verify forgot password functionality | Successful | Jan 13: Testing started Jan 15: Error occurs Jan 18: The error has been fixed. The Forgot Password feature is already functioning well, both in terms of OTP generation and password reset.
8 | Admin must be able to log out | Admin Log out | Successful | Jan 18: Started testing Jane 19: I can successfully log out now
Requirements Traceability
Matrix